## T.o.v.road rep.
| 2019-2020 Tax-On-Vehicles | [9 empty] | Tax-On- Vehicle
Sl No. | Name of The work | Ward No | Head | G.O. No. & Dt. | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Amount Put to Tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Paid Amount | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of cmpltion

## BEUP
BEUP 2019-2020
Sl No | Name of The work | W. No | Head | GO No. | Length/Area | MB No & Page | Name Of Contractor | Tender No. & Date | Sanctioned Amount | Estimated Amount | Amount put to tender | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V. No. | Bill Amount | Balance | Security Deposit | Income Tax | CGST | SGST | W.Cess | Net Amount | Dt. Of compltn.
| Construction of Toilet in Horizon Basti (6, No. Bagan) Ward No. 11 | 11 | Toilet horizon bustee | 14029/1/2016-DPLO/151978 DATED. 23.05.2018 |  | 562/73-82 | Tapan Chatterjee | 69/KM/PW/BEUP/18-19 |  | 464818 | 464818 |  | 1st R/A. | 014561 | 01.04.19 | 6 | 228134 |  | 22813 | 4563 | 2281 | 2281 | 2281 | 193915 | 27.07.18-14.08.18
| Installation of High pole with lights(per pole) at a) Junction of Mahadeb ghosal road & Joykrishna Ghosal road wardno. 9 b) Junction of Jadunath Mukherjee road & Iswar Chandra Banerjee Lane ward no. 9 & 10 c) Junction of Iswar Chandra Banerjee Lane, Kalinath ghosal road & Jadunath Mukherjee road(Seba Samity) ward no 9 d) In front of Poushali Samity ward no. 9 e) Junction of Chunilal Banerjee road, AC banerjee road & PC banerje road (near chatal Math) ward no. 12 f)B.L ghosh road (near-yubak sangha club) ward no 8, 11 g) Junction of Bachaspati Para & RN Tagore road near Axis Bank ward no. 13 h) Green Park three point crossing ward no. 22 i) Crossing of KP ghosal road & Thakurdas Banerjee road ward no. 21,22 j) Nandan Nagar Amtala Junction ward no. 31 d) Infront of Nandan Nagar Girls school ward no. 31,32 k) Infront of Nandan Nagar Girls school ward no.31,32 l) BC Chatterjee Street, Vivekananda Park- in front of Lokenath Villa Flat ward no. 17 m) Ramkrishna Mission road & Ranjan Goswami Sarani Junction (Badal Das more) ward no 34,35 n) Ramkrishna Mission road & Ranjan Goswami Sarani Junction (Near- Jatindas 5 no. Uchho rasta) ward no 34,35 o) Ramkrishna Mission road & Bandhab Nagar junction in front of Jatin Das Kali Mandir ward no. 34 p) MM feeder road near Horijon Basti ward no. 11 q) Nilratan Adhikary Road near- Phoolbagan Balutola junction ward no. 3 r) Mill approach road & Sabji Bagan junction ward no. 2 s) Dhobia bagan in front of siraz Panwala shop ward no. 4,7 t) Chai maidan & Platia line junction near Hauda ward no. 4. u) Uttar Basudevpur Madhya pally near puja mandop ward no. 29 v) Adarshapally junction ward no. 25 w) Sahid Mahal Junction ward no. 28 x) Sabji bagan near Trenching ground ward no. 24 y) Bankim Pally & BL ghosh road junction ward no. 11 z) Jadunath Sarbobhoumya lane and TN biswas road junction ward no. 14 z') Basudebpur road near Shibtala puja Mandop ward no. 29. |  | High Pole | 14029/1/2016-DPLO/151978 DATED. 23.05.2018 | pole-16 Set | 514/144-152 | Chandra Construction | Tender ID: 2018_MAD_183176_1, Tender Ref. No. WBMAD/KM/BEUP/NIT-10(e)/2018-19(3rd Call) |  | 1838846 |  | 1287192 | 1st R/a. | 014566 | 02.05.19 | 392 | 721536 |  | 72154 | 14431 | 7215 | 7215 | 7215 | 613306 | 26.12.18-07.02.19
949670

## MPLAD
| MPLAD 2018-2019 | [7 empty] | MPLAD -2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. | Length Mtr./Area M | Area Sqm. | MB No & Page | Name Of Contractor | Tender No. & Date | Sanctioned Amount | Released Amont | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Balance Amount | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of cmpltn | Bal in CGST
| Installation of LED based street light in ward no.10 under Kmarhati Municipality | 10 |  | D-13013/3/2014-DPLO/158564 Dt.16/01/2019 | 79 Nos. |  | 595/1-3 | R.D.Industrial | 195/KM/PW/MPLAD/18-19 Dt.19/02/19 | 263250 |  | 351550 |  | 351550 | 1st R/A. & Final | 014559 | 01.04.19 | 3 | 263250 | 88100 |  | 5265 | 2633 | 2633 | 2633 | 250086 | 03.03.19-07.03.19
| Illumination of Street light in Ward No.22 under Kamarhati Municipality | 22 |  | D-13013/3/2014-DPLO/158564 Dt.16/01/2019 | 50 Nos. |  | 595/4-6 | R.D.Industrial | 196/KM/PW/MPLAD/18-19 Dt.19/02/19 |  |  | 491650 |  | 491650 | 1st R/A. & Final | 014559 | 01.04.19 | 4 | 366750 | 124900 |  | 7335 | 3668 | 3668 | 3668 | 348411 | 08.03.19-15.03.19
| Construction and developmnt of Club Infrastructure and Gymnasium of Ariadaha Sporting Club at Motilal Park, 6 Kedar Nath Singha Road, Ariadaha, Kolkata - 700 057 |  | Club | G.O. D-13013/4/2014-DPLO/157335 Date :- 14.12.18 |  |  | 381/107-115 | Bhabatarini Builders | Tender Title: WBMAD/KM/MPLAD/NIT-24 (e)/2018-19 Tender Id: 2018_MAD_203712_1 | 865177 |  | 1153569 |  | 1146071 | 1st R/A. | 014560 | 01.04.19 | 5 | 467996 |  | 46800 | 9360 | 4680 | 4680 | 4680 | 397796 | 22.02.19-07.03.19
| Construction of Building of Ariadaha Sarbamangala Balika Vidyalaya, 25, Jaikrishna Ghoshal Road, Ariadaha, Kol - 57, Ward no. - 9, Kamarhati Municipality, North 24 parganas. | 9 | School Building | 13016/10/2012-DPLO/152335, Dt:05.06.18 |  |  | 585/34-42 | Bhowmi-con | 113/KM/PW/MPLAD/18-19 Dt.23/08/18 |  | 406295 | 418484 | 402232 | 1st R/a. & Final | 1st R/A. | 014562 | 01.04.19 | 7 | 359867 |  | 35987 | 7197 | 3599 | 3599 | 3599 | 305886 | 29.10.18-17.11.18
| Construction of Community Hall at Rabindra Nagar in Ward No.16 under Kamarhati Municipality | 16 | Community Hall | D-10313/3/2014-DPLO/154852 Dt.21/08/18 |  |  | 504/28-35 | S.B Enterprise | 115/KM/PW/MPLAD/18-19 Dt.18/09/18 |  | 284260 | 292788 | 284260 | 1st R/a. & Final | 1st R/a. & Final | 014575 | 11.06.19 | 514 | 250000 | 33200 |  | 5000 | 2500 | 2500 | 2500 | 237500 | 30.10.18-29.11.18
| Installation of High pole and lights in different places in ward no.09 under Kamarhati Municipality, North 24 Parganas | 9 | Hih Pole |  |  |  | 595/11-17 | R.D.Industrial | 197/KM/PW/MPLAD/18-19 Dt.19/02/19 |  | 421216 |  | 421216 | 1st R/A. & Final |  |  |  |  | 403391 |  |  | 8068 | 4034 | 4034 | 4034 | 383221 | 30.03.19-11.04.19

## Swachh Bharat
Compactor Station 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. No. & Dt. | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Amount Put to Tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Paid Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare Cess | Net Amount | Dt. Of cmpltion

## Sagar Dutta
Development of Municipal Area -Sagar Dutta MCH - 2019-2020
Sl No. | Name of The work | Ward No | Head | Area | MB No & Page | G.O. | Name Of Contractor | Tender No. & Date | Released Amount | Estimated Amount | Amount put to tender | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare Cess | Net Amount | Dt. Of compltn.
1 | [16 empty] | 467915 |  |  | 30607 | 4679 |  | 4679 | 427950 | 23.07.17

## Spot sources
Spot Sources - 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. | Length in Mtr.Area in Sqm | MB No & Page | Name of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Security Deposit | Income Tax | Sales Tax | W.Cess | Net Amount | Dt. Of compltn.
1 | [15 empty] | 35757 |  |  |  |  | 35757
1293.75
9918.75
345
1035
7935

## 3rd SFC
|  | 3rd State Finance Commission 2019-2020 | [23 empty] | m
Sl.no. | Name of The work | Ward No | Head | G.O. | Length in Mtr.Area in Sqm | Area | MB No & Page | Name of Contractor | Tender No. & Date | Amont put to tender | Estimated Amount | Tendered Amount | Type of Bill | Ch No. / T.V.No. | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of compltn. | Bal. of cgst
| Const. of 3 nos. Vat, 1no Culvert, 10 nos.slab at Bhagaban Mondal st. & other places under W-8 | 8 | Vat & Slab | G.O.No:294(Sanction)/UDMA-13014(14)/1/2018-BDG-MASEC, Dated:04.10.18 |  |  | 314/182-197 | Ibrahim Realty | 119/KM/PW/SFC/18-19 Dt.21/01/2018 | 193582 | 199332 | 193582 | 1st R/A. | 20190400000065 | 03.04.19 |  | 84612 |  |  | 8461 | 1692 | 846 | 846 | 846 | 71921 | 28.01.19-14.02.19
| Supplying & fixing of wooden laminet storages in PWD under Kamarhati Municipality | 16 | cc road |  |  |  | 557/137-140 | sristi interior & exterior | 203/KM/PW/SFC/18-19 Dt.25/02/2019 | 514917 | 499920 | 494921 | 1st R/A. & Final | 20190400000199 | 10.04.19 |  | 487574 |  |  | 48757 | 9751 | 4876 | 4876 | 4876 | 414438 | 05.03.19-18.03.19
| Proposed drain diversion at 9 B.T.Road beside staff quarter in ward no.16 | 16 | Drain Diversion |  | 12 |  | 573/23-29 | Charulata | 147/KM/PW/SFC/18-19 Dt.04.02.19 | 118621 | 122144 | 118621 | 1st R/A. & Final | 20190400000432 | 26.04.19 |  | 107432 |  |  | 10743 | 2149 | 1074 | 1074 | 1074 | 91318 | 19.02.19-29.02.19
| Renovation of drains under ward no.31 1) Netaji Pally block-D starting from H/o. Mukul Pal to Nantu Sarkar 2) Office Para 1st Lane starting from opp. of Subash Sangha to H/o. Kanu Das 3) Amtala starting from Roy Medico to H/o.Mr. Aich | 31 | Drain |  | Drain 200.05 | 92.26 road | 566/44-58 | M.K. Construction | NIT NO : WBMAD/KM/SFC/NIT- 32(e)/2018-19 TENDER ID :2O 19_MAD_2O9075_7 | 1174673.63 | 1209565 | 1169388 | 1st R/A. | 201905000000536 | 06.05.19 |  | 587368 |  |  | 58737 | 11747 | 5874 | 5874 | 5874 | 499262 | 22.02.19-18.03.19
| Construction of 9 Nos. concrete road at Udayvilla bye lane starting from Shankar Palit, Dulal Das, Uday Villa pally Committee, Ranu Biswas , Asit Sarkar. Reba Rani Das, Shambhunath Dey & Tamal Dey under Ward No.24 | 24 | CC ROAD |  |  |  | 469/190-200 | Mitra construction | 137/KM/PW/SFC/18-19 Dt.04.02.19 | 436782 | 449756 | 434598 | 1st r/A. | 201905000000581 | 08.05.19 |  | 294564 |  |  | 29456 | 5891 | 2946 | 2946 | 2946 | 250379 | 03.12.18-04.01.19
| Beautification of Bat Tola Park installation of new decorative fittings in ward no.28 under Kamarhati Municipality | 28 | Decorative Lighting |  | 26 Nos. |  | 595/7-10 | R.D. Industrial | 202/KM/PW/SFC/18-19 Dt.25/02/2019 | 452852 | 466305 | 452852 | 1st R/A. & Final |  |  |  | 451470 |  |  | 45147 | 9029 | 4515 | 4515 | 4515 | 383749
| Construction of Guard Wall at besides Dantia Kahl southern side of Thakur Bagan in Ward No.16 | 16 | GUARD WALL |  | 18 |  | 573/17-22 | Charulata | 146/KM/PW/SFC/18-19 Dt.04.02.19 | 126973 | 130744 | 126973 | 1st R/A. & Final |  |  |  | 123814 |  |  | 12381 | 2476 | 1238 | 1238 | 1238 | 105243 | 11.02.19-18.02.19

## S.F.C.
State Finance Commission 2019-2020
| Name of The work | Ward No | Head | G.O. | Length in Mtr.Area in Sqm | Area | MB No & Page | Name of Contractor | Tender No. & Date | Amont put to tender | Estimated Amount | Tendered Amount | Type of Bill | Ch No. / T.V.No. | Cheque Date | V.No. | Bill Amount | Balance | Security Deposit | Income Tax | CGST | SGST | Welfare tax | Net Amount | Dt. Of compltn.
1 st R/A & Final

## Road Repairing
ROAD REPAIRING 2019-2020
Sl.No. | Name of The work | Ward No | Head | G.O. | Length in Mtr.Area in Sqm | Area | MB No & Page | Name of Contractor | Tender No. & Date | Amont put to tender | Estimated Amount | Tendered Amount | Type of Bill | Ch No. / T.V.No. | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare tax | Net Amount | Dt. Of compltn.

## kmda drain
Sl No. | Name of The work | Ward No | Head | G.O. | Length in Mtr. | Area in Sqm | MB No & Page | Name of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No/T.V.No. | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare tax | Net Amount | Completion Date
1 | Construction of Surface drain at Abdul Latif Street starting from L.P.No. 7/4 to Chatterjee Para Puja Mandap under Ward No.22. | 22 | Drain |  | 158.3 |  | 568/23-34 | Malay Kundu | TENDER ID No. 2018_MAD_ 160802_1 (2ND CALL) NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 , op. dt:03.02.18 | 5,58,005.00 |  | 5,19,000.00 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 449037 |  |  | 44904 | 8981 | 4490 | 4490 | 4490 | 381682 | 03.05.18-02.06.18
2 | Construction of covered surface drain at Old Nimta road to North DumDum Border under Ward No.33. | 33 | Surface Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 193.5 |  | 478/169-182 | Ray's Construction | TENDER ID No. 2018_MAD_147556_25 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 , Dt:23.02.18 | 1164755 |  | 1128065 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 1119899 |  |  | 111990 | 22398 | 11199 | 11199 | 11199 | 951914 | 18.04.18-30.05.18
3 | Construction of Nikashi drain at Chowdhurypara starting from H/O. Surya Singh to Ajay Paul's grocerry shop under Ward No.29. | 29 | Nikashi Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 329.3 |  | 567/23-34 | Banik Construction | TENDER ID No. 2018_MAD_147556_21 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18, op.dt:03.02.18 | 952805 |  | 923265 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 752414 |  |  | 75241 | 15048 | 7524 | 7524 | 7524 | 639553 | 08.03.18-04.04.18
4 | Construction of Nikashi drain at Sree Pally main road (both side) starting from Sahid Mahal pond to H/O. Sri. Swapan Das under Ward No.28. | 28 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 355.9 |  | 578/17-40 | Sumit Paul | TENDER ID No. 2018_MAD_147556_18 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 14,66,419.00 |  | 14,27,559.00 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 1365194 |  |  | 136519 | 27304 | 13652 | 13652 | 13652 | 1160415 | 15.05.18-14.08.18
6 | Construction of Nikashi drain at Military Road starting from Dwaipayan Pally to Belgharia Byamagar Club under Ward No.28. | 28 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 360.2 |  | 578/1-16 | Mahadeb Das | TENDER ID No. 2018_MAD_147556_19 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 11,88,809.00 |  | 11,60,889.00 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 1135592 |  |  | 113559 | 22712 | 11356 | 11356 | 11356 | 965253 | 08.03.18-14.05.18
7 | Construction of covered surface drain along Old Nimta road starting from Ananda Nagar more to Tarun Tirtha Club under Ward No.32. | 32 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 169.8 |  | 495/160-182 | B.Ghosh & Sons | TENDER ID No. 2018_MAD_160802_2 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 11,64,755.00 |  | 10,89,628.00 | 1st R/A. Final | 20190400000096 | 04.04.19 |  | 1070558 |  |  | 107056 | 21411 | 10706 | 10706 | 10706 | 909973 | 02.05.18-04.06.18
8 | Construction of Surface drain at Eastern side of Mission Road under Ward No.35. | 35 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 407.2 |  | 583/1-13 | BLUKON | TENDER ID No. 2018_MAD_147556_27 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 15,10,157.00 |  | 14,64,701.00 | 1st R/A. & Final | 20190400000096 | 04.04.19 |  | 1459216 |  |  | 145922 | 29184 | 14592 | 14592 | 14592 | 1240334 | 20.08.18-12.10.18
9 | Construction of Nikhasi drain starting from Ariadaha Matrimangal to Dakshineswar High School under Ward No.10 & 12. | 10 & 12 | Nikashi Drain |  | 326.85 |  | 577/1-21 | Rudra Enterprise | TENDER ID No. 2018_MAD_147556_04 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 1797355 |  | 1743614 | 1st R/A. | 20190400000096 | 04.04.19 |  | 1070044 |  |  | 107004 | 21401 | 10700 | 10700 | 10700 | 909539 | 05.03.18-27.04.18
10 | Construction of drain at Tulsidanga Lane from Tea Shop of Jiban Babu at D.D.Mondal Ghat Road to L.P.No. 5/13/2 under Ward No.15. | 15 | Drain | G.O.NO:3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 86.5 |  | 521/63-68 | D.B.Enterprise | TENDER ID No. 2018_MAD_147556_09 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 4,60,818.00 |  | 4,46,302.00 | 1st R/A. | 20190400000096 | 04.04.19 |  | 279065 |  |  | 27907 | 5581 | 2791 | 2791 | 2791 | 237204 | 12.11.18-15.11.18
11 | Construction of Nikashi drain at Old Nimta Road (South Side) starting from 2,No. Rail Way Gate to N.K.Chatterjee Street Bye Lane under Ward No.21. | 21 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 343.85 |  | 564/18-30 | A.M.S. Enterprise | TENDER ID No. 2018_MAD_147556_12 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 12,15,250.00 |  | 1176484 | 1st R/A. Final | 20190400000130 | 05.04.19 |  | 1159265 |  |  | 115927 | 23185 | 11593 | 11593 | 11593 | 985374 | 12.03.18-20.04.18
12 | Construction of Nikashi drain at Nandan Nagar starting from Amtola crossing to H/O. Sri. Debdas Sarkar under Ward No.31. | 31 | Nikashi Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 398.65 |  | 494/180-196 | S.B. Enterprise | TENDER ID No. 2018_MAD_147556_22 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 , op. dt:03.02.18 | 1583855 |  | 1540299 | 1st R/A. Final | 20190400000130 | 05.04.19 |  | 1338798 |  |  | 133880 | 26776 | 13388 | 13388 | 13388 | 1137978 | 02.04.18-21.05.18
14 | Construction of Nikashi drain at B.N.Ghosal Road (both side) starting from 7,No. B.N.Ghosal Road to Shib Mandir under Ward No.21. | 21 | Nikashi Drain |  |  |  | 505/160-175 | N.A. Construction | TENDER ID No. 2018_MAD_147556_11 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 6,85,979.00 |  | 6,65,400.00 | 1st R/A. | 20190400000130 | 05.04.19 |  | 562005 |  |  | 56201 | 11240 | 5620 | 5620 | 5620 | 477704 | 02.05.18-04.06.18
15 | Construction of Nikashi drain at Nandan Nagar road (southern side) starting from H/O. Sri. Sankar Das to Prince Tower under Ward No.32. | 32 | Nikashi Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 315 |  | 490/132-145 | Construction of India | TENDER ID No. 2018_MAD_147556_23 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 1188095 |  | 1149428 | 1st R/A. Final | 20190400000130 | 05.04.19 |  | 1053371 |  |  | 105337 | 21067 | 10534 | 10534 | 10534 | 895365 | 21.03.18-20.04.18
16 | Construction of Nikhasi drain wall at M.M.Feeder Road (Southern Side) starting from Ariadaha Post Office to N.C.Chatterjee Street under Ward No.10. | 10 | Nikashi Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 452.5 |  | 538/170-189 | Aritra Enterprise | TENDER ID No. 2018_MAD_147556_03 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18,op.dt:03.02.18 | 1797355 |  | 1743974 | 1st R/A. | 20190400000130 | 05.04.19 |  | 1042090 |  |  | 104209 | 20842 | 10421 | 10421 | 10421 | 885776 | 16.03.18-08.05.18 | 1042090
17 | Construction of Nikhasi drain at B.L.Ghosh Road (Southern Side) starting from Tetultala Road to 11 No. Ward Office under Ward No.11. | 11 | Nikashi Drain |  | 353.7 |  | 577/22-40 | Rabindra Nath Chatterjee | TENDER ID No. 2018_MAD_147556_05 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 1797355 |  | 1743614 | 1st R/A. | 20190400000130 | 05.04.19 |  | 992631 |  |  | 99263 | 19853 | 9926 | 9926 | 9926 | 843737 | 02.05.18-22.06.18
18 | Construction of Nikashi drain at North Basudebpur Madhyapara main road starting from opp. Of Trivasha Academy to Texmaco road under Ward No.29. | 29 | Nikashi Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 310 |  | 578/41-75 | Majumder & Co. | TENDER ID No. 2018_MAD_147556_20 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 28,56,467.00 |  | 27,65,917.00 | 1st R/a. & Final | 20190400000169 | 08.04.19 |  | 2466523 |  |  | 246652 | 49330 | 24665 | 24665 | 24665 | 2096546 | 16.08.18-15.11.18
19 | Construction of Nikhasi drain at U.N.Mukherjee Road (eastern side) starting from Sarada Math ti Phari under Ward No.12. | 10 | BT Road | 276(Sanction)MA/P/C-10/1G-9/2017 DT.18/08/2017 | 210 | 1117.96 | 780/59-68 | Aritra Enterprise | TENDER ID No. 2018_MAD_147556_06 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 , op.dt: 20.11.17 | 17,97,355.00 |  | 17,49,366.00 | 1st R/A. & Final | 20190400000169 | 08.04.19 |  | 1409531 |  |  | 140953 | 28191 | 14095 | 14095 | 14095 | 1198102 | 07.06.18-15.07.18
20 | Construction of Nikashi drain at A.A.Pai Road (both side) starting from B.M.Banerjee Road to Khal under Ward No.20. | 20 | Nikashi Drain |  | 385.85 |  | 511/112-124 | Ashok Bose | TENDER ID No. 2018_MAD_147556_10 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18, op.dt:03.02.18 | 1076230 |  | 1040822 | 1st R/A. & Final | 20190400000169 | 08.04.19 |  | 743451 |  |  | 74345 | 14869 | 7435 | 7435 | 7435 | 631932 | 15.03.18-21.04.18
21 | Construction of Roadside drain at Lenin Nagar from H/O.Dasarath Khetry to H/O. Rajani Pradhan under Ward No.15. | 15 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 250.1 |  | 541/36-43 | Ashes Sanyal | TENDER ID No. 2018_MAD_147556_08 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 6,36,294.00 |  | 6,17,269.00 | 1st R/A. & Final | 20190400000169 | 08.04.19 |  | 602851 |  |  | 60285 | 12057 | 6029 | 6029 | 6029 | 512422 | 05.09.18-05.10.18
22 | Construction of Piped drain at eastern side of boundary wall of Adyapith from 75m chanage to house no. 15 under Ward No.13. (Length-150m) | 10 &11 | Piped Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 145.6 |  | 780/36-45 | Gour Gopal Roy | TENDER ID No. 2018_MAD_147556_07 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 , op.dt:03.02.18 | 6,06,376.00 |  | 590671 | 1st R/A. Final | 20190400000169 | 08.04.19 |  | 566562 |  |  | 56656 | 11331 | 5666 | 5666 | 5666 | 481577 | 20.07.18-03.08.18
23 | Construction of Surface drain along OLD Nimta Road starting from junction Nilganj Road to Joymala Bhandar under Ward No.25. | 25 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 197.6 |  | 579/42-55 | P.P. Construction | TENDER ID No. 2018_MAD_147556_16 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 980306 |  | 950407 | 1st R/A. Final | 20190400000169 | 08.04.19 |  | 869408 |  |  | 86941 | 17388 | 8694 | 8694 | 8694 | 738997 | 25.07.18-27.08.18
24 | Construction of Surface drain along Old Nimta Road starting from Junction of Nabin Pally (Culvert) to Junction of Panchanantola Road under Ward No.22. | 22 | Surface drain | G.O.NO:3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | De130.55, slAB-77.50 |  | 579/57-71 | Utpal Roy | TENDER ID No. 2018_MAD_147556_13 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 1356723 |  | 1315343 | 1st R/A. | 20190400000198 | 10.04.19 |  | 745679 |  |  | 74568 | 14914 | 7457 | 7457 | 7457 | 633826 | 29.08.18-06.10.18
25 | Construction of Surface drain along Nilganj Road starting from junction of Military Road (L.P.No. 59/8/2) to junction of Senerah Road under Ward No.24. | 26 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 431.3 |  | 579/1-19 | Mahadeb Majumder enterprize | TENDER ID No. 2018_MAD_147556_15 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 2145260 |  | 2077684 | 1st R/A. Final | 20190400000198 | 10.04.19 |  | 2063259 |  |  | 206326 | 41265 | 20633 | 20633 | 20633 | 1753769 | 05.03.18-15.06.18
5 | Construction of drainage wall at Anwar Bagan from Milan-e-Young Star to Khatal of Ansari in Ward No. 06 under Kamarhati Municipality (Length-250 M) | 6 | Drainage wall | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 250 |  | 578/76-87 | Ma Muktokeshi Enterprise | TENDER ID No. 2018_MAD_147556_02 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 13,97,870.00 |  | 1365020 | 1st R/a. | 20190400000096 | 04.04.19 |  | 777441 |  |  | 77744 | 15549 | 7774 | 7774 | 7774 | 660826 | 16.11.18-18.12.18
13 | Construction of drain starting from opp. Of Public Medical Hall at N.R.Adhikary Road via Craig Street to Graham Road in W.No. 03. | 28 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 |  |  | 394/136-151 | K.G.N. Traders | TENDER ID No. 2018_MAD_147556_01 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 27,86,877.00 |  | 27,04,664.00 | 1st R/A. Final | 20190400000130 | 05.04.19 |  | 1682391 |  |  | 168239 | 33648 | 16824 | 16824 | 16824 | 1430032 | 14.03.18-10.05.19
26 | Construction of Surface drain along OLD Nimta Road starting from Joymala Bhandar to Tetultola More under Ward No.26. | 26 | Drain | 3710-UD/P/M/B/2F-167/2017, dt:20.11.2017 | 269.6 |  | 579/20-41 | Sudip Talukder | TENDER ID No. 2018_MAD_147556_17 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 1316179 |  | 1276036 | 1st R/A. Final | 20190400000431 | 26.04.19 |  | 1225546 |  |  | 122555 | 24511 | 12255 | 12255 | 12255 | 1041715 | 18.06.18-24.07.18
| Construction of Nikhasi drain at U.N.Mukherjee Road (eastern side) starting from Sarada Math ti Phari under Ward No.12. | 12 | Drain |  |  |  | 580/147-160 | Aritra Enterprise | TENDER ID No. 2018_MAD_147556_06 NIT No. WBMAD/KM/KMDA/N.I.T-15(e)/2017-18 | 17,97,355.00 |  | 1749366 | 2nd R/A. & Final |  |  |  | 324356 |  |  | 32436 | 6487 | 3244 | 3244 | 3244 | 275701 | 08.01.19-29.01.19
28326177
885776
-60

## 13th Finance
13TH Finance 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. | Length | Area | MB No & Page | Name of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | W.Cess | Net Amount | Dt. Of compltn.

## metro1
| Dev. Of Municipal Area (Rehabilitation Project for Extension of Metro) | [6 empty] | METRO 2019-2020 |  | Fund received:67300000 | [7 empty] | 58905536
Sl No. | Name of The work | Ward No | Head | G.O. Name & Date | Length | Rea | MB No & Page | Name Of Contractor | Tender No. & Date | Sanc,. Am. | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Bal. Amount | Security Deposit | Income Tax | Sales Tax | W.Cess | Net Amount | Comp. Date
#REF!
| GO.NO. | DATE | AMOUNT
| 387-WT(F)/TR/P/TOIP-15/2015, Dt: 09.10.15 | 09.10.15 | 35300000
| 218-WT(F)/TR/P/TOIP-15/2015, Dt: 07.07.17 | 07.07.17 | 32000000
67300000

## 14th Finance
14TH FINANCE - 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. No. & Date | Length | Area | MB No & Page | Name of Contractor | Tender No. & Date | Release Amount | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | CGST | SGST | W.Cess | Net Amount | Dt. Of compltn.
| Const. of 3 nos. Vat, 1no Culvert, 10 nos.slab at Bhagaban Mondal st. & other places under W-8 | 8 | Vat & Slab | G.O.No:294(Sanction)/UDMA-13014(14)/1/2018-BDG-MASEC, Dated:04.10.18 |  |  | 314/182-197 | Ibrahim Realty | 119/KM/PW/SFC/18-19 Dt.21/01/2018 |  | 193582 | 199332 | 193582 | 1st R/A. | 20190400000065 | 03.04.19 |  | 84612 |  |  | 8461 | 1692 | 846 | 846 | 846 | 71921 | 28.01.19-14.02.19
| Construction of Conc. Road at B.T.Road Bye Lane beside Satam Sivam Appartmentin Ward No.16. | 16 | cc road |  | 35.3 |  | 574/10-17 | Sumit Paul | 93/KM/PW/14TH FIN/18-19 Dt.29/08/18 |  | 178620 | 183978 | 177280 | 1st R/A. & Final | 288652 | 29.04.19 | 388 | 173615 |  |  | 17362 | 3472 | 1736 | 1736 | 1736 | 147573 | 03.12.18-04.01.19
| Patch repairing of bituminous road at B.M.Banerjee Road starting from Feeder Road ton R.B.I under Ward No. 18,19 & 20. | 18,19&20 | BT Road |  | 82.35 | 578.53 | 528/194-198 | Utpal Roy | 90/KM/PW/14TH FIN/18-19 Dt.29/08/18 |  | 86850 | 89431 | 86416 | 1st R/a. & Final | 288653 | 29.04.19 | 387 | 81725 |  |  | 8173 | 1635 | 817 | 817 | 817 | 69466 | 16.09.18-20.09.18
| Construction of drainage wall at May Dibas Pally road besides Manasa Mandir in Ward No. 14. | 14 | Drainage wall |  | 106.1 |  | 465/46-51 | S.R.B. construction | 94/KM/PW/14TH FIN/18-19 Dt.29/08/18 |  | 136334 | 139088 | 135652 | 1st R/A. & Final | 288680 | 11.06.19 | 512 | 136632 |  |  | 13663 | 2733 | 1366 | 1366 | 1366 | 116138 | 24.09.18-04.10.18
| Construction of Pay and Use Toilet at Belgharia Auto Stand under Ward No. 20 & 21. | 20 & 21 | Pay & Use toilet | 347/(Sanction)/MA/C-10/3S-14/2015 (Pt-1) Dated. 29.12.2016 |  |  | 486/179/197 | Ray's Construction | 269/KM/PW/14th Finance/17-18, Dt: 08/06/17 |  | 462326 | 476195 | 462326 | 2nd R/A. & Final | 288682 | 19.06.19 | 554 | 266571 |  |  | 26657 | 5331 | 2666 | 2666 | 2666 | 226585 | 18.02.19-17.03.19
| Supplying & Fixing of wooden laminate work stations in PWD under Kamarhati Municipality | 16 | Wooden work at PWDepartment |  |  |  | 306/176-179 | Sristi Interior & Exterior | 02/KM/PW/14th Fin/19-20 Dt.24/06/19 |  | 456439 | 469997 | 454157 | 1st R/A. & Final |  |  |  | 454157 |  |  | 45416 | 9083 | 4542 | 4542 | 4542 | 386032 | 28.06.19-08.07.19

## ULB & DEPARTMENTAL
| 2019-2020 | [5 empty] | ULB & DEPARTMENTAL
Sl No. | Name of The work | Ward No | Head | L/Area | MB No & Page | Name Of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Balance | Security Deposit | Income Tax | CGST | SGST | Welfre Cess | Net Amount | Dt. Of cmpltion

## BMS
BMS -2019-2020
| Name of The work | Ward No | Head | G.O. | Length/Area | Area | MB No & Page | Name Of Contractor | Tender No. & Date | release amnt | Amount put to tender4 | Estimated Amount | Tendered Amount | Type of Bill | Cheque No. / T.V. No. | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | CGST | SGST | W.Cess | Net Amount | Dt. Of cmpltn
6754845

## Road Damage repairing
Sl No. | Name of The work | Ward No | Head | G.O. No. & Date | Length | Area | MB No & Page | Name of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | Balance | Security Deposit | Income Tax | Sales Tax | W.Cess | Net Amount | Dt. Of compltn.

## Green City
Green City Project 2019-2020
[20 empty] | 0 | 0 | 0 | 0 | 0 | 0
Sl No. | Name of The work | Ward No | Head | G.O. | Length in Mtr. | Area in Sqm | MB No & Page | Name of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No/T.V.No. | Cheque Date | V.No. | Bill Amount | Balance | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare tax | Net Amount
| Children Park at Gitanjali Road under Kamarhati Municipality, Ward No- 15. | 15 | Park |  |  |  | 584/1-29 | Maa Muktokeshi Enterprise | TENDER ID N0. 2018_MAD_149366_5 N.I.T No. WBMAD/KM/N.I.T-12(e) /2017-18 | 2014389 |  | 17,52,317.00 | 2nd R/A. | 20190400000062 | 02.04.19 |  | 859809 |  |  | 85981 | 17196 | 8599 | 8599 | 8599 | 730835 | 02.08.18-02.11.18
| Protection of the Lokenath Pukur with beautification under kamarhati Municipality |  | Lokenath pukur |  |  |  | 546/32-40 | Balaji Enterprise | TENDER ID N0. 2018_MAD_149366_7 N.I.T No. WBMAD/KM/N.I.T-12(e) /2017-18 (3rd call) | 3805169 | 3986887.94 | 3295276 | 1st R/a. | 20190400000062 | 02.04.19 |  | 1157195 |  |  | 115720 | 23144 | 11572 | 11572 | 11572 | 983615 | 09.11.18-27.12.18
2017004
1 st R/A & Final

## DEv. of Municipal Area(SP fund)
Development of Municipal Area - 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. No. | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Release Amount | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of compltn. | Bal of CGST
1 st R/A & Final

## Implementation of various schem
Implementation of Various scheme - 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Estimated Amount | Amount put to tender | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of compltn.
| Construction of Bituminous Road at K.C.C Mitra St. bye lane and Anandagarh main road under Ward No.26. | 26 | BT Road | (AA & FS G.O. No: 779/UDMA-13014(12)/66/2018-BDG-MA SEC Dt.25/06/18 116(Sanction)/UDMA-13014(12)/66/2018-BDG MA SEC Dt.25/06/18 | 84.7 | 791.66 | 546/41-49 | Prabir Kumar Chateerjee | Tender ID: 2018_MAD_170618_21/Tender Ref. No. WBMAD/KM/D.M.A/NIT-03(e)/2018-19. |  | 334982 | 924933 | 1st R/A. & Final | 20190400000062 | 02.04.19 |  | 320952 |  |  | 32095 | 6419 | 3210 | 3210 | 3210 | 272808 | 02.01.19-21.01.19
| Development of Sitalatala Street (Bituminous) starting from Ambika Mukherjee Road to B.C. Chatterjee Road in Ward No.17 | 17 | BT Road | (AA & FS G.O. No: 779/UDMA-13014(12)/66/2018-BDG-MA SEC Dt.25/06/18 116(Sanction)/UDMA-13014(12)/66/2018-BDG MA SEC Dt.25/06/18 | 321.2 |  | 515/107-114 | Rabindra Nath Chatterjee | NIT NO : WBMAD/KM/DMA/NIT-12(e)/2018-19 TENDER ID : 2018_MAD_179592_31 | 819412 | 852188 | 815192 | 1st R/A. & Final | 20190400000431 | 26.04.19 |  | 793721 |  |  | 79372 | 15874 | 7937 | 7937 | 7937 | 674664 | 15.11.18-30.1.18
| Construction of 9 Nos. concrete road at Udayvilla bye lane starting from Shankar Palit, Dulal Das, Uday Villa pally Committee, Ranu Biswas , Asit Sarkar. Reba Rani Das, Shambhunath Dey & Tamal Dey under Ward No.24 | 24 | CC ROAD |  |  |  | 469/190-200 | Mitra construction | 137/KM/PW/SFC/18-19 Dt.04.02.19 | 436782 | 449756 | 434598 | 1st r/A. |  |  |  | 294564 |  |  | 29456 | 5891 | 2946 | 2946 | 2946 | 250379 | 14.02.19-14.03.19
| Construction of Nikashi drain along Osworld Housing Estate boundary wall starting from Matri Pally under Ward No.23. | 23 | Drain |  | 170 | 238 | 584/30-43 | Naumani Enterprise | Tender ID: 2018_MAD_177148_6/Tender Ref. No. WBMAD/KM/D.M.A/NIT-04(e)/2018-19.(2nd Call) (SL-06) | 1022812 |  | 99082 | 1st R/A. & Final | 201905000000535 | 06.05.19 |  | 958151 |  |  | 95815 | 19163 | 9582 | 9582 | 9582 | 814427 | 06.08.18-28.12.18 | 1-34
| Construction of Proposed/Renovation surface drain with Raising of Concrete Road at Bindhyabasinitala Road A.N. Chatterjee Street By Lane D.D. Mondal Ghat Road Bylane H/O Arun Mukherjee and K.P Mukherjeeby lane and P.C. Banerjee by lane and P.C. Banerjee by lane near H/o Haru Adhikary H/o Dhrubatara Das H/O Subrata Ghosh, near Modak Sweets under Ward No.12. | 12 | Drain | (AA & FS G.O. No: 779/UDMA-13014(12)/66/2018-BDG-MA SEC Dt.25/06/18 116(Sanction)/UDMA-13014(12)/66/2018-BDG MA SEC Dt.25/06/18 | 374.8 | 202.37 | 580/117-131 | Sudip Talukder | NIT NO : WBMAD/KM/DMA/NIT-12(e)/2018-19TENDER ID : 2018_MAD_179592_3 | 938163 | 975690 | 923856 | 1st R/A. & Final | 20190400000431 | 26.04.19 |  | 833535 |  |  | 83354 | 16671 | 8335 | 8335 | 8335 | 708505
| Construction of Drain and Conc. Road at (1) K.N.Banerjee Bye Lane H/O. Bankim Mondal to North end of passage (2) B.B.Tola Road to H/o. Gandhi Mondal (3) 38, D.D.Mondal Ghat Road to H/o. Maya Das Gupta under Ward No. 13. | 13 | Drain & CC Road | 526/MA/P/C-10/3S-90/2017(Pt.) Dt. 18/04/2018 | 173.65 |  | 386/89-101 | Banik Construction | Tender ID: 2018_MAD_177146_4/Tender Ref. No. WBMAD/KM/D.M.A/NIT-03(e)/2018-19 (2nd Call) (SL-04) | 600166 |  | 591163 | 1st R/A. & Final |  |  |  | 502891 |  |  | 50289 | 10058 | 5029 | 5029 | 5029 | 427457 | 03.01.19-22.01.19
| Construction of Drain and Conc. Road at (1) K.N.Banerjee Bye Lane H/O. Bankim Mondal to North end of passage (2) B.B.Tola Road to H/o. Gandhi Mondal (3) 38, D.D.Mondal Ghat Road to H/o. Maya Das Gupta under Ward No. 13. | 24 | Drain & CC Road | 526/MA/P/C-10/3S-90/2017(Pt.) Dt. 18/04/2018 | 173.65 |  | 386/89-101 | Banik Construction | Tender ID: 2018_MAD_177146_4/Tender Ref. No. WBMAD/KM/D.M.A/NIT-03(e)/2018-19 (2nd Call) (SL-04) |  | 600166 | 591163 | 1st R/A. & Final |  |  |  | 502891 |  |  | 50289 | 10058 | 5029 | 5029 | 5029 | 427457 | 03.01.19-22.01.19
| Development of concrete road at Nandannagar New colony 5th.,6th.,& 7th. bye lane starting from H/O Manik Duuta to H/O Harihar. Dutta, H/o. Biplab Biswas to H/o. Tapan Mishra, H/o. Jagadish Sikder to H/o. Dr. R. N. Roy under Ward No. - 30. | 30 | CC Road | (AA & FS G.O. No: 779/UDMA-13014(12)/66/2018-BDG-MA SEC Dt.25/06/18 116(Sanction)/UDMA-13014(12)/66/2018-BDG MA SEC Dt.25/06/18 | 195.55 | 430.91 | 568/55-64 | Malay Kundu | WBMAD/KM/DMA/NIT-12(e)/2018-19 TENDER ID : 2018_MAD_179592_20 | 391922 |  | 387925 | 1st R/a. & Final |  | 384684 |  | 198000 | 186684 |  |  | 3960 | 1980 | 1980 | 1980 | 188100 | 31.08.18-19.09.18
| Development of Bituminous Road at D.D.Mondal Ghat Road starting from K.N.Banerjee Road to D.D.Mondal Ghat under Ward No. 12. | 12 | BT Road |  | 630 | 2575.74 | 481/156-170 | Aritra Enterprise | Tender ID: 2018_MAD_177146_3/Tender Ref. No. WBMAD/KM/D.M.A/NIT-03(e)/2018-19.(2nd Call) (SL-03) |  | 816756 | 806138 | 1st & Final |  |  |  | 424000 | 342591 |  |  | 8480 | 4240 | 4240 | 4240 | 402800 | 20.07.18-14.08.18

## N.U.H.M.
N.U.H.M. 2019-2020
Sl No. | Name of The work | Ward No | Head | Area | MB No & Page | G.O. | Name Of Contractor | Tender No. & Date | Released Amount | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | cgst | sgst | Welfare Cess | Net Amount | Dt. Of compltn.
1 | Construction of Two Storied New UPHC Building Within Premises No.- , Jatin Das Nagar, Block -4, Mouza-Belghoria, J.L.No.-3, C.S.Dag No.- 1750 (P), Ward No.-35, E.P. No- , Holding No.- & P.S.-Belgharia, Dist.-24pgs(N), Under Kamarhati Municipality. | 35 | UPHC Building | DH & FWS/N.U.H.M/88G/2017/117 Dt. 16/01/17 |  |  | 503/103-160 | Othentic | Tender Ref.No. WBMAD/KM/NIT- 01(e)/2017-18 (SL-1) Tender Id. 2017_MAD_108199_1 | NUHM | 44,14,971.00 | 43,37,709.00 | 2nd R/A. | 123937 | 22.04.19 |  | 450000 | 1290398 |  |  | 9000 | 4500 | 4500 | 4500 | 427500 | 03.03.18-03.05.18
1740398
913751
1740398

## AMRUT
AMRUT 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. No. & Date | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Saction amount | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of compltn.
| Construction of Proposed park at B.L. GHOSH ROAD at ward no.-11 under Kamaehati Municipality | 11 | Park |  |  |  | 589/1-14 | Progressive Construction | NIT NO: WBMAD/KM/AMRUT/NIT-15(e)/2018-19 TENDER ID : 2018_MAD_180623_1 |  | 286301 | 294890 | 286301 | 1st R/A. | 007157 | 01.04.19 | 2 | 313023 |  |  | 31302 | 6260 | 3130 | 3130 | 3130 | 266071 | 25.09.18-12.10.18
| Construction of Proposed Park at "JATINDAS NAGAR BLOCK - 4" under Kamarhati Municipality, Ward No.35 | 35 | Park | G.O.no.438(39)/MA/AMRUT/E-6/2015(Pt-IV) dt.28.06.18 | 18.7 | 98.176 | 522/120-128 | BLUKON | NIT NO : WBMAD/KM/AMRUT/NIT-15(e)/2018-19TENDER ID : 2018_MAD_184431_1(2nd Call) | 195759 | 986190 |  | 978793 | 1st r/A. | 007158 | 07.05.19 | 294 | 208544 |  |  | 20854 | 4171 | 2085 | 2085 | 2085 | 177264 | 01.11.18-04.01.19
| Construction of Proposed Park at Matri Pally under Kamarhati Municipality, Ward No.31 | 31 | Park | 438(39)/MA/AMRUT/E-6/2015(Pt-IV) dt.28.06.18 |  |  | 537/94-108 | Sumit Paul | NIT NO : WBMAD/KM/AMRUT/NIT-15(e)/2018-19 TENDER ID : 2018_MAD_180623_3 | 343923 | 1753814 |  | 1719615 | 1st r/A. | 007158 | 07.05.19 | 295 | 343923 | 98521 | 442444 |  | 6878 | 3439 | 3439 | 3439 | 326728 | 12.11.18-26.12.18
| Construction of Park at "ARUNODAY PALLY" under Kamarhati Municipality, Ward No.30 | 30 | Park | 438(39)/MA/AMRUT/E-6/2015(Pt-IV) dt.28.06.18 |  |  | 537/109-117 | Hundred Days Agency | NIT NO : WBMAD/KM/AMRUT/NIT-15(e)/2018-19 TENDER ID : 2018_MAD_180623_2 | 202157 | 1030361 |  | 1010784 | 1st r/A. | 007158 | 07.05.19 | 196 | 202157 | 82865 |  |  | 4043 | 2022 | 2022 | 2022 | 192048 | 28.12.18-31.01.19
| Construction of Three Storied Annex Building of Amrita Bhavan over existing incomplete Ground floor under Kamarhati Municipality under Ward No. 17. | 17 | Three Std. Annex Building | 89/MA/AMRUT/F-2/2016, Dt. 04.04.2017.(AMRUT)(2nd Call) |  | 89.65 | 517/70-163 | S.C. Ghosh | Tender ID. 2017_MAD_11682_6(2nd Call) /Tender Ref. No.WBMAD/KM/NIT-03(e)/2017-18 (2nd Call) (SL-6) |  | 33,79,043.00 |  | 3346942 | 2nd R/A. |  |  |  | 1645616 |  |  | 164562 | 32912 | 16456 | 16456 | 16456 | 1398774 | 10.01.18-05.02.18

## SSM
SSM 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Released Amount | Estimated Amount | Amount put to tender | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare Cess | Net Amount | Dt. Of compltn.

## HFA
HFA- 2019-2020
Sl No. | Name of The work | Ward No | Head | G.O. No. & Date | Length | Area | MB No & Page | Name Of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Security Deposit | Income Tax | CGST | SGST | Welfare Cess | Net Amount | Dt. Of compltn.
1 | Preparation of detail Project Report(2018-2019) -DPR and printing of 4sets report under HFA Project | [6 empty] | Centre for Research & Development | invoice:CRD/1902, Dt:04.02.19 | [7 empty] | 317500

## Ferry Ghat
Ferryghat 2019-2020
Sl No. | Name of The work | Ward No | Head | Length /Nos. | Area | G.O. No. & Date | MB No & Page | Name Of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare Cess | Net Amount | Dt. Of compltn.
#REF!

## Fund transfer
Ferryghat 2019-2020
Sl No. | Name of The work | Ward No | Head | Length /Nos. | Area | G.O. No. & Date | MB No & Page | Name Of Contractor | Tender No. & Date | Amount put to tender | Estimated Amount | Tendered Amount | Type of Bill | Cheque No | Cheque Date | V.No. | Bill Amount | balance Amount | Material Cost | Security Deposit | Income Tax | Sales Tax | Welfare Cess | Net Amount | Dt. Of compltn.

## Sheet2
HFA